## Sheet1
Task | Start | Finish | Completion %
Task 1: Individual Investigation of Possible Project Topics | 2024-10-20 | 2024-10-20 | 0.1
Task 2: Topic Chosen by Team | 2024-10-21 | 2024-10-21 | 0.2
Task 3: Identify stakeholders and issues. | 2024-10-22 | 2024-10-22 | 0.3
Task 4: Agree upon the stakeholder(s) and issue(s) each team member will investigate further. | 2024-10-22 | 2024-10-22 | 0.4
Task 5: Begin to make slides. | 2024-10-23 | 2024-10-23 | 0.5
Task 6: Further investigation by individual team members, alternative courses of action and the effects from perspective of stakeholder | 2024-10-24 | 2024-10-24 | 0.6
Task 7: Correlate perspectives and make a decision. | 2024-10-25 | 2024-10-25 | 0.7
Task 8: As a team, use a weighted benefit analysis to show how you made your decision. | 2024-10-26 | 2024-10-27 | 0.8
Task 9: Slides compiled for team presentation. | 2024-10-28 | 2024-10-29 | 0.9
Task 10: Presentation during the lab period. | 2024-10-30 | 2024-10-30 | 1
1